## Sprints
Sprint | Start | Finish | Scope/Goals
1 | 2023-02-28 | 2023-02-28 | Greenfield: - studying of DICOM protocol - testing Sonador platform locally Brownfield: - setting up testing environment - installing DCM Uploader software
2 | 2023-03-01 | 2023-03-14 | Greenfield: - understand Sonador Gateway - setting up a testing dataset Brownfield: - testing DCM Uploader transmissions - try to reproduce the problems
3 | 2023-03-15 | 2023-03-28 | Greenfield: - testing DICOM transmissions with Sonador Brownfield: - invetigate why DCM Uploader restarts often without aparent reason - understand its source code - plan further test series
4 | 2023-03-29 | 2023-04-11 | Greenfield: - understanding Sonador’s strengths and limitations - setting up a full scale test environment Brownfield: - stucked on DCM Uploader malfunctions and sudden freezes - although successfully sent a few files, fail to complete a full study transmission - not able to refactor the entangled source code - Finally, decided to move on from the solution
5 | 2023-04-12 | 2023-04-25 | - Proof of concept with third-party libraries: Pydicom, DCM4che and Orthanc
6 | 2023-04-26 | 2023-05-09 | - Comparison of DCM4Che and Orthanc solutions
7 | 2023-05-10 | 2023-05-23 | - DCM4Che x Orthanc: performance tests
8 | 2023-05-24 | 2023-06-06 | - DCM4Che x Orthanc: integration and secutirty tests
9 | 2023-06-07 | 2023-06-20 | - Enhancements in both solutions
10 | 2023-06-21 | 2023-07-04 | - Systematic tests in both solutions to asses error proneness and performance: DCM4chee wins
11 | 2023-07-05 | 2023-07-18 | - Orthanc: live demonstration with the sponsors
12 | 2023-07-19 | 2023-08-01 | - Development, integration and tests of VPN solutions
13 | 2023-08-02 | 2023-08-15 | - DCM4che: live demonstration with the sponsors
14 | 2023-08-16 | 2023-08-29 | - Cloud tests: AWS - POC containernet
15 | 2023-08-30 | 2023-09-12 | - Orthanc: studies removal after transmissions - Dcm4che: mirror component to allow zero-visibility transmissions
16 | 2023-09-13 | 2023-09-26 | - Dcm4che x Orthanc: overall comparison. - Decision made to adopt Orthanc and discontinue Dcm4che
17 | 2023-09-27 | 2023-10-10 | - Orthanc: new architecture design: Uploader Manager API and View - Transmission logs
18 | 2023-10-11 | 2023-10-24 | - Uploader Manager and View prototypes
19 | 2023-10-25 | 2023-11-07 | - Uploader Manager API - Wireguard VPN integration
20 | 2023-11-08 | 2023-11-21 | - Uploader Manager View
21 | 2023-11-22 | 2023-12-05 | - Integration tests - Step-by-step config and tests demo
22 | 2023-12-06 | 2023-12-19 | - Code refactoring - Full solution demo
23 | 2023-12-20 | 2024-01-03 | - Transmissions metrics and statistics
24 | 2024-01-04 | 2024-01-16 | - Local PACS forwarding - Admin role session and dashboards
25 | 2024-01-17 | 2024-01-30 | - Final presentation to the sponsor
26 | 2024-01-31 | 2024-02-27 | - Bugs fixing and reports writing